# FitDuel — Implementation Plan

Draft roadmap: build order, module breakdown, and phased timeline for the push-up MVP.

# Architecture Decision to Make First

The current prototype is Python + OpenCV, desktop-only. FitDuel itself is web-first, and the product intentionally never streams anyone's camera feed anywhere - so pose detection needs to run in the browser, not on the server.

MediaPipe ships a JS/WASM build of the same Pose Landmarker (the @mediapipe/tasks-vision npm package, also available via CDN) that runs client-side in real time. The prototype's logic - the calibration hold, elbow/back angle math, plank-orientation check, and smoothing - carries over conceptually; it's a port to TypeScript against the JS API, not a restart from zero.

This also cleanly explains the event-driven design: the browser detects reps locally and only ever sends small events such as { repCompleted: true, valid: true, confidence: 0.92 } to the server - never video.

# Module Breakdown

| # | Module | Owns | Depends on |
| --- | --- | --- | --- |
| 1 | AI Engine | Pose detection, rep-validity logic, structured event output | Nothing (foundation) |
| 2 | Web Client | Camera capture, in-browser AI engine, match UI, live score display | AI Engine's event contract |
| 3 | Core API | Auth, user profiles, ratings storage (FastAPI + Postgres) | Nothing (can start early) |
| 4 | Realtime Match Engine | WebSocket server, Redis match state, score sync, match lifecycle | Core API (users), AI Engine's event contract |
| 5 | Matchmaking | Queue, MMR-based pairing | Core API, Rating module |
| 6 | Rating System | ELO updates, rank tiers, MMR | Core API, Match Engine |
| 7 | Anti-Cheat | Server-side plausibility checks on reported reps | Match Engine |
| 8 | Infra / DevOps | Docker, CI, branch strategy, environments | Nothing (can start Day 1) |
| 9 | Docs / Product | PRD, rep-validity rules, API/WS contracts, ADRs | Nothing (should start Day 1) |

# Why This Order

The founding idea already states the priority: prove that push-up detection can be measured accurately before anything else. Everything downstream - matches, ratings, matchmaking - is worthless if reps aren't measured fairly, and CV accuracy is also the one piece with no existing playbook to lean on, unlike the backend/frontend/infra work. Standard risk-first practice is to spend the earliest time on the least-proven, highest-uncertainty part of the system, not the most familiar part.

# Proposed Timeline

Assumes one focused engineer on the AI/core path. *Phase 2b can run alongside Phase 2 if a second engineer is available - it doesn't need to wait. Treat week numbers as relative ordering and effort rather than a fixed calendar - adjust for actual team size and availability.

| Phase | Weeks | Module(s) | Deliverable / exit criteria |
| --- | --- | --- | --- |
| 0 | 1 (first 2-3 days) | Docs, Infra | Repo + branch strategy live; 1-page rep-validity rules doc; Docker skeleton. Keep this short - don't let it become a multi-week phase. |
| 1 | 1-3 | AI Engine | Port prototype logic to @mediapipe/tasks-vision (TypeScript); wrap as a module returning structured events (rep_completed, valid, confidence). Build a test harness: 15-20 sample clips across body types/lighting/camera angles with known ground-truth counts. Exit criteria: acceptable accuracy on the test set, not just "looks fine in one demo." |
| 2 | 3-5 | Web Client (solo mode) | Browser captures webcam, runs the AI Engine, shows live rep count and Good rep / paused feedback - no networking yet. First real go/no-go checkpoint for the product. |
| 2b* | 3-5 | Core API, Infra | Auth, user model, Postgres schema for users/matches/ratings, even if unused yet. Doesn't depend on CV accuracy, so a second engineer can build this alongside Phase 2. |
| 3 | 5-7 | Realtime Match Engine | WebSocket server, Redis match state, two-browser-tabs test: client sends rep events, server is source of truth, opponent's score updates live. |
| 4 | 7-8 | Matchmaking | Queue + MMR-proximity pairing. Start with one MMR number serving both visible rating and hidden MMR; split them later once there's real data, rather than hard-coding the eventual formula now. |
| 5 | 8-9 | Rating System | ELO update on match end, rank tiers for display. |
| 6 | 9-10 | Anti-Cheat (basic) | Server-side sanity checks: max plausible reps/second, reject events with impossible timing gaps. Deeper anti-cheat is post-MVP. |
| 7 | 10-12 | Real-user testing | 5-10 people with different bodies/rooms/lighting actually duel. This surfaces CV edge cases no test harness catches - budget real iteration time, not just a token testing week. |

That's roughly 10-12 weeks to a genuinely testable MVP (one exercise, two real people dueling, fair-ish scoring) - not counting leaderboards, seasons, additional exercises, or mobile, which are already correctly scoped as later.

# Concrete Next 2 Weeks

- Days 1-3: write the 1-page rep-validity rules doc (largely already defined by the Python prototype's logic) and finish repo/branch setup.

- Days 4-14: stand up a bare-bones HTML/TypeScript page using @mediapipe/tasks-vision, port the elbow-angle, plank-orientation, and calibration logic from the Python prototype, and get it counting reps for one person in a browser tab. That single milestone - browser-based rep counting working at all - is the real proof of concept, more so than anything built after it.

# Assumptions & Caveats

- Team size and availability are unknown, so the week estimates above are relative effort, not a committed schedule.

- The AI Engine accuracy target (Phase 1's exit criteria) should be defined concretely - e.g. a target precision/recall against the test-clip set - before moving to Phase 2, so "done" isn't a judgment call.

- Hidden MMR and visible rating are intentionally left as a single number for v1, per the founding document's own instruction not to prematurely hard-code the eventual formula.